## Sheet1
|  | Weeks | [9 empty] | Scenario Inputs
ID | Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | number of people |  | 30
| Initiating | [10 empty] | fees |  | 700
1 | Assign project manager | [10 empty] | enrolment |  | 6
2 | Develop project charter | [10 empty] | flyer cost |  | 0.5
3 | Meet with stakeholders | [10 empty] | flyer number ordered |  | 6000
| Planning | [10 empty] | mail |  | 4500
4 | Create scope plan | [10 empty] | postage |  | 0.55
5 | Create WBS and schedule | [10 empty] | drinks and lunch |  | 30
6 | Create procurement plan | [10 empty] | Manuals |  | 50
7 | Create Project Mgmt. Plan | [10 empty] | development time (hrs) |  | 150
| Executing | [10 empty] | Projects Revenues
8 | Develop network configuration | [10 empty] | fees |  | 21000
9 | Remove all HW | [10 empty] | total revenues |  | 42000
10 | Order SW and HW
11 | Install new SW on servers | [10 empty] | projected expenses fixed
12 | Install new HW and SW on client’s machines | [10 empty] | rent |  | 600
13 | Test new billing system | [10 empty] | Enrolment setup fees |  | 450
| Controlling | [10 empty] | advertising |  | 300
14 | Status reports | [10 empty] | sub total |  | 1350
15 | Update plans
| Closing | [10 empty] | variable
16 | Lessons learned | [10 empty] | enrolments |  | 180
17 | Prepare final report | [10 empty] | flyers |  | 3000
[12 empty] | mail and postage |  | 2475
[12 empty] | beverages and lunch |  | 900
| critical paths | [10 empty] | manuals |  | 1500
[12 empty] | sub total |  | 8055
| 2 + 2.5 + 5 + 5 + 5 + 5 + 5 + 5 | 34.5 | [9 empty] | Total Expenses |  | 51405
shortest amount of time to complete this task is 34.5 days
| 2 + 2.5 + 5 + 5 + 5 + 5 + 5 + 5 | 34.5 | [9 empty] | Projected Profit |  | 685
[12 empty] | Personal Time Value |  | 4.75
[12 empty] | Total after profits |  | 50577.5
| Assign Project Manager |  |  |  | Status Reports
| start: 03/10/2022 |  | id: 1 |  | start: | 2022-10-07 | id: 14
| finish: 05/10/2022 |  | dur: 2 |  | finish: |  | dur: 5
[5 empty] | Develop Project Charter |  |  |  | Meet with stakeholders
[5 empty] | start: | 2022-10-07 | id: 2 |  | start: | 2022-10-12 | id: 3
[5 empty] | finish: 12/10/2022 |  | dur: 2.5 |  | finish: | 2022-11-30 | dur: 30
[5 empty] | Create scope plan |  |  |  | Create WBS and schedules |  |  |  | Create procurement plan
[5 empty] | start: 7/10/2022 |  | id: 4 |  | start: 12/10/2022 |  | id: 5 |  | start: 18/10/2022 |  | id: 6
[5 empty] | finish: 12/ 10/2022 |  | dur: 2.5 |  | finish: 18/10/2022 |  | dur: 5 |  | finish: 24/10/2022 |  | dur: 5
[9 empty] | Create project management plan |  |  |  | Update plan
[9 empty] | start: 12/10/2022 |  | id: 7 |  | start: 16/11/2022 |  | id: 15
[9 empty] | finish: 16/11/2022 |  | dur: 20 |  | finish: 2/12/2022 |  | dur: 12.5
[13 empty] | lessons learnt |  |  | prepare final report
[13 empty] | start: 16/11/2022 |  | id: 16 | start: 24/11/2022 | id: 17
[13 empty] | finish: 24/11/2022 |  | dur: 5 | finish: 01/12/2022 | dur: 7.5
[9 empty] | Develop network configuration |  |  |  | Remove all HW |  |  | Order SW & HW |  | Install new SW on servers |  | Install new HW and SW on client’s machines |  | Test new billing system
[9 empty] | start: 12/10/2022 |  | id: 8 |  | start: 18/10/2022 |  | id: 9 | start: 25/10/2022 | id: 10 | Start: 01/11/2022 | id: 11 | start: 09/11/2022 | id: 12 | start: 17/11/2022 | id: 13
[9 empty] | finish: 18/10/2022 |  | dur: 5 |  | finish: 25/10/2022 |  | dur: 5 | finish: 01/11/2022 | dur: 5 | finish: 08/11/2022 | dur: 5 | finish: 16/11/2022 | dur: 5 | finish: 24/11/2022 | dur: 5