## Sheet1
|  | Weeks | [9 empty] | Scenario Inputs
ID | Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  | number of people
| Initiating | [10 empty] | fees
1 | Assign project manager | [10 empty] | enrolment
2 | Develop project charter | [10 empty] | flyer cost
3 | Meet with stakeholders | [10 empty] | flyer number ordered
| Planning | [10 empty] | mail
4 | Create scope plan | [10 empty] | postage
5 | Create WBS and schedule | [10 empty] | drinks and lunch
6 | Create procurement plan | [10 empty] | Manuals development time (hrs)
7 | Create Project Mgmt. Plan
| Executing | [10 empty] | Projects Revenues
8 | Develop network configuration | [10 empty] | fees
9 | Remove all HW | [10 empty] | total revenues
10 | Order SW and HW
11 | Install new SW on servers | [10 empty] | projected expenses fixed
12 | Install new HW and SW on client’s machines | [10 empty] | rent
13 | Test new billing system | [10 empty] | Enrolment setup fees
| Controlling | [10 empty] | advertising
14 | Status reports | [10 empty] | sub total
15 | Update plans
| Closing | [10 empty] | variable
16 | Lessons learned | [10 empty] | enrolments
17 | Prepare final report | [10 empty] | flyers
mail and postage
| Initiating |  |  | Planning |  |  | Executing |  |  |  |  | beverages and lunch
| start: 03/10/2022 | ID: 1 |  | start: 04/10/2022 | ID: 2 |  | start: 18/10/2022 | ID: 3 |  |  |  | manuals
| finish: 03/10/2022 | Due: 1 day |  | finish: 17/10/2022 | Due: 10 days |  | finish: 28/11/2022 | Due: 29 days |  |  |  | sub total
Total Expenses
Closing
[7 empty] | start: 29/11/2022 | ID: 4 |  |  |  | Projected Profit
[7 empty] | finish: 6/12/2022 | Due: 5 days
Personal Time Value
| 1 | 1 = 1 | 2 | 2 = 10 | 3 | 3 = 29 | 4 | 4 = 5 | 5 (finish) | 45 days
| Assign Project Manager |  |  |  | Status Reports
| start: 03/10/2022 |  | id: 1 |  | start: | 2022-10-07 | id: 14
| finish: 05/10/2022 |  | dur: 2 |  | finish: | 2022-10-12 | dur: 5
[5 empty] | Develop Project Charter |  |  |  | Meet with stakeholders
[5 empty] | start: | 2022-10-07 | id: 2 |  | start: | 2022-10-12 | id: 3
[5 empty] | finish: | 12/10/202022 | dur: 2.5 |  | finish: | 2022-11-30 | dur: 30
[5 empty] | Create scope plan |  |  |  | Create WBS and schedules |  |  |  | Create procurement plan
[5 empty] | start: 7/10/2022 |  | id: 4 |  | start: 12/10/2022 |  | id: 5 |  | start: 18/10/2022 | id: 6
[5 empty] | finish: 12/ 10/2022 |  | dur: 2.5 |  | finish: 18/10/2022 |  | dur: 5 |  | finish: 24/10/2022 | dur: 5
[9 empty] | Create project management plan |  |  |  | Update plan
[9 empty] | start: 12/10/2022 |  | id: 7 |  | start: 16/11/2022 | id: 15
[9 empty] | finish: 16/11/2022 |  | dur: 20 |  | finish: 2/12/2022 | dur: 12.5
[13 empty] | lessons learnt |  | prepare final report
[13 empty] | start: 16/11/2022 | id: 16 | start: 24/11/2022 | id: 17
[13 empty] | finish: 24/11/2022 | dur: 5 | finish: 01/12/2022 | dur: 7.5
[9 empty] | Develop network configuration |  |  |  | Remove all HW |  | Order SW & HW |  | Test new billing system |  | Install new SW on servers |  | Install new HW and SW on client’s machines
[9 empty] | start: 12/10/2022 |  | id: 8 |  | start: 18/10/2022 | id: 9 | start: 25/10/2022 | id: 10 | Start: 01/11/2022 | id: 13 | start: 09/11/2022 | id: 11 | start: 17/11/2022 | id: 12
[9 empty] | finish: 18/10/2022 |  | dur: 5 |  | finish: 25/10/2022 | dur: 5 | finish: 01/11/2022 | dur: 5 | finish: 08/11/2022 | dur: 5 | start: 16/11/2022 | dur: 5 | finish: 24/11/2022 | dur: 5